## Project Planner
Real Time Embedded Programming Project Planner
Team 2: Sleep Panda |  |  | Team Member: |  | Chengsen Dong, Yihan Wang, Rui Liu, Hui Wang
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 13 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete
[9 empty] | Actual (beyond plan) | [5 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | TEACHING WEEKS
[6 empty] | 2023-01-11 | 2023-01-18 | 2023-01-25 | 2023-02-01 | 2023-02-08 | 2023-02-15 | 2023-02-22 | 2023-03-01 | 2023-03-08 | 2023-03-15 | 2023-03-22 | 2023-03-29 | 2023-04-05 | 2023-04-12 | 2023-04-19
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Form Teams | 1 | 3 | 1 | 2 | 100%
Pitching session | 1 | 3 | 2 | 2 | 100%
Basic development environment configuration | 4 | 3 | 3 | 2 | 90%
Buzzer Driver Development | 5 | 2 | 4 | 1 | 100%
MAX30101 Driver Development | 5 | 2 | 5 | 3 | 100%
4K 30FPS camera development | 6 | 1 | 6 | 2 | 80%
Sound Sensor Driver Development | 7 | 2 | 7 | 3 | 100%
WM8960 Driver Development | 7 | 2 | 8 | 4 | 85%
Production costing | 7 | 5 | 7 | 6 | 100%
Ink screen driver development | 8 | 4 | 8 | 5 | 75%
MLX90640 Driver Development | 7 | 4 | 8 | 6 | 70%
Social Media Promotion | 7 | 9 | 8 | 7 | 95%
Software Architecture | 8 | 4 | 6 | 5 | 100%
Assembling Unit Code | 10 | 5 | 12 | 2 | 95%